## Product backlog
Backlog Manager
Prio | Feature/Theme | Title | Story | Notes | Demo | Release tag | Story Pts | Status
New
Sort

## ProgramAssessment
Scoring: 0 - Never, 1 - Rarely 2 - Occasionally, 3 - Often, 4 - Very Often, 5 - Always
Area / Question | Score |  | Comments
Product Ownership Health
Product Owner facilitates user story development, prioritization and negotiation | 5
Product Owner collaborates proactively with Product Management and other stakeholders | 5
User Stories are small, estimated, functional and vertical | 5
Product owner facilitates development of acceptance criteria which are used in planning, review and story acceptance | 5
Teams groom the backlog every sprint | 5
Total Product Health Score | 25 | 100%
PSI/Release Health
Team participates fully in Release Planning and Inspect and Adapt | 5
Product backlog for the PSI is itemized and prioritized | 5
Teams proactively interact with other teams on the train as necessary to resolve impediments | 5
Team participates in System Demo every two weeks, illustrating real progress towards objectives | 5
Team reliably meet 80-100% of non-stretch PSI Objecives | 5
Total PSI/Release Health Score | 25 | 100%
Sprint Health
Team plans the sprint collaboratively, effectively and efficiently | 5
Team always has clear sprint goals, in support of PSI objectives, and commits to meeting them | 5
Teams apply acceptance criteria and Definition of Done to story acceptance | 5
Team has a predictable, normalized velocity which is used for estimating and planning | 5
Team regularly delivers on their sprint goals | 5
Total Sprint Health Score | 25 | 100%
Team Health
Team members are self-organized, respect each other, help each other complete sprint goals, manage interdependencies and stay in-sync with each other | 2
Scrummaster attends Scrum of Scrums and interacts with RTE as appropriate | 2
Stories are iterated through the sprint with multiple define-build-test cycles (e.g. the sprint is not a waterfalled) | 2
Team holds collaborative, effective and efficient planning and daily meetings where all members participate, status is given clearly, issues are raised, obstacles are removed and information exchanged | 2
Team holds a retrospective after each sprint and makes incremental changes to continually improve its performance | 2
Total Team Health Score | 10 | 40%
Technical Health
Teams actively reduce technical debt in each sprint | 5
Team has clear guidance and understanding of intentional architecture guidance, but is free and flexible enough to allow emergent design to support optimal implementation | 5
Automated acceptance tests and unit tests are part of story DoD | 5
Refactoring is always underway | 5
CI, build and test automation infrastructure is improving | 5
Total Technical Health Score | 25 | 100%
Total Project Team Score | 110 | 88%
Summary Questions
Radar Chart Data
Product Ownership Health | 1
PSI/Release Health | 1
Sprint Health | 1
Team Health | 0.4
Technical Health | 1
Program Assesment

## ReleaseCycleAssessment
Scoring: 0 - Never, 1 - Rarely 2 - Occasionally, 3 - Often, 4 - Very Often, 5 - Always
Area / Question | Score |  | Comments
Planning Readiness
Top ten features are prioritized ahead of time using WSJF | 2.5
Program backlog is ready and socialized with Product Owners and key stakeholders 1-3 weeks prior to event | 2.5
Product owners have team backlogs groomed and ready | 2.5
Vision presentation is ready and reviewed prior to event | 2.5
Architects are extending runway by identifying upcoming architectural features, socialized with teams prior to event, update domain model | 2.5
RTE has prepared and announced events, agenda, attendance, venue, access provisions, specialty events, continuing education, as appropriate | 2.5
Total Planning Readiness Score | 15 | 50%
Release Planning Event
Event has effective facilities and distributed team communications | 2.5
Program stakeholders, business owners, and shared resources are in attendance | 2.5
All team members participate, in person or remotely | 2.5
Business context, Product vision, and Top 10 features are effectively communicated | 2.5
Timeboxes are adhered to; event starts and ends on time | 2.5
Risks are discussed, addressed categorized | 2.5
Management addresses key scope and quality challenges and makes adjustments as necessary | 2.5
Alignment is achieved: All teams leave with agreed to, SMART team PSI objectives, ranked by business value, approved by business owners, published to all stakeholders | 2.5
Confidence vote is 3 or higher | 2.5
Total Release Planning Event Score | 22.5 | 50%
PSI Execution
Scrum of Scrums meets routinely and effectively | 2.5
Release Management assist and adjusts scope; communicates expectations internally and externally, provides necessary governance authority | 2.5
Scope is appropriately managed; adjustments made primarily at sprint boundaries | 2.5
RTE is effective in facilitating and reporting progress | 2.5
Continuous integration, including automated tests happen at the system level | 2.5
Fortnightly System Demo is routine and effective | 2.5
System team is effective in its role | 2.5
Teams proactively interact outside of SoS to address dependencies, impediments and resolve issues | 2.5
Total PSI Execution Score | 20 | 50%
PSI Results
Full solution progress is demonstrated | 2.5
Each team reports on actual accomplishments vs. PSI objectives | 2.5
Release predictability measure is routinely measured and reported | 2.5
Program delivers between 80-100% of non-stretch objectives | 2.5
Program collects and trends agreed to metrics | 2.5
Total PSI Results Score | 12.5 | 50%
Inspect and Adapt
Session is held every PSI | 2.5
Most team members attend | 2.5
Key stakeholders attend | 2.5
Improvement stories are identified and itemized | 2.5
Improvement stories are incorporated into release planning event | 2.5
Session is effectively facilitated | 2.5
Total Inspect and Adapt Score | 15 | 50%
Stakeholder Engagement
Program is self-organizing and self-managing | 2.5
Release Management Team is functional and effective | 2.5
Product management is agile, engaged, functional and effective throughout PSI | 2.5
Development management plays a supportive, empowering role and eliminates impediments outside of programs control | 2.5
Total Stakeholder Engagement Score | 10 | 50%
Portoflio Alignment
Program is self-organizing and self-managing | 5
Release Management Team is functional and effective | 5
Product management is agile, engaged, functional and effective throughout PSI | 5
Total Portfolio Alignment Score | 15 | 100%
Total Release Train Score | 110 | 53.66%
Radar Chart Data
Planning Readiness | 0.5
Release Planning Event | 0.5
PSI Execution | 0.5
PSI Results | 0.5
Inspect and Adapt | 0.5
Stakeholder Engagement | 0.5
Total Portfolio Alignment Score | 1
Release Cycle Assessment

## BurnDown-ScopeMgmt
Progress | 100 | 80 | 60 | 40 | 15
Scope Changes | 0 | 0 | 0 | -15 | -25

## Release Burndown
| Start Date for First Sprint of Release | 2013-08-10
| Days per Sprint: | 14
| Number of Sprints in Release: | 16
| Total Story Points Remaining: | 86 | 86
Sprint Ending Dates
ID | Story Title | 2013-08-10 | 2013-08-24 | 2013-09-07 | 2013-09-21 | 2013-10-05 | 2013-10-19 | 2013-11-02 | 2013-11-16 | 2013-11-30 | 2013-12-14 | 2013-12-28 | 2014-01-11 | 2014-01-25 | 2014-02-08 | 2014-02-22 | 2014-03-08 | 2014-03-22
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Story Points Remaining
1 | Story 1 | 2013-08-10: 5; 2013-08-24: 5
2 | Story 2 | 2013-08-10: 3; 2013-08-24: 3
3 | Story 3 | 2013-08-10: 8; 2013-08-24: 8
4 | Story 4 | 2013-08-10: 8; 2013-08-24: 8
5 | Story 5 | 2013-08-10: 12; 2013-08-24: 12
6 | Story 6 | 2013-08-10: 13; 2013-08-24: 13
7 | Story 7 | 2013-08-10: 21; 2013-08-24: 21
8 | Story 8 | 2013-08-10: 8; 2013-08-24: 8
9 | Story 9 | 2013-08-10: 8; 2013-08-24: 8
Insert New Rows Above this Line
| Projected Burndown Increment (each Sprint) | 2013-08-10: 5.375
| Projected Target Track | 86 | 80.625 | 75.25 | 69.875 | 64.5 | 59.125 | 53.75 | 48.375 | 43 | 37.625 | 32.25 | 26.875 | 21.5 | 16.125 | 10.75 | 5.375 | 0

## Win-Caluclator
Copy and paste the corresponding sections from the workbook you want to validate into the sections below. | [11 empty] | Interim Calculated Values Used Below |  |  |  | Estimation Accuracy Lookup
Card Priority | Short Name | Commit Type | Source | Original Estimate | Approval |  | Day of Sprint |  |  |  |  | Actual | Found | Estimate Delta | Estimate Correct? | Actual | Correct
[5 empty] | Yes/No | Day | Thu | Fri | Mon | Tue | Wed |  |  |  |  | 1 | 1
1 | Card 1 | Planned | New Feature | 5 | Yes | Wed |  | 2 | 2 | 1 | 1 | 6 | 1 | 1 | Yes | 2 | 2
2 | Card 2 | Planned | Defect | 8 | Yes | Wed |  | 1 | 3 | 2 | 2 | 8 | 0 | 0 | Yes | 3 | 3
3 | Card 3 | Planned | New Feature | 3 | Yes | Tue | 1 | 2 |  |  |  | 3 | 0 | 0 | Yes | 4 | 5
4 | Card 4 | Planned | New Feature | 5 | Yes | Wed | 2 | 2 | 2 | 1 | 1 | 8 | 3 | 3 | No (8) | 5 | 5
5 | [11 empty] | -- | -- | -- | -- | 6 | 5
6 | [11 empty] | -- | -- | -- | -- | 7 | 8
7 | [11 empty] | -- | -- | -- | -- | 8 | 8
8 | [11 empty] | -- | -- | -- | -- | 9 | 8
9 | [11 empty] | -- | -- | -- | -- | 10 | 8
10 | [11 empty] | -- | -- | -- | -- | 11 | 13
11 | [11 empty] | -- | -- | -- | -- | 12 | 13
12 | [11 empty] | -- | -- | -- | -- | 13 | 13
13 | [11 empty] | -- | -- | -- | -- | 14 | 13
14 | [11 empty] | -- | -- | -- | -- | 15 | 13
15 | [11 empty] | -- | -- | -- | -- | 16 | 13
16 | [11 empty] | -- | -- | -- | -- | 17 | 21
17 | [11 empty] | -- | -- | -- | -- | 18 | 21
18 | [11 empty] | -- | -- | -- | -- | 19 | 21
19 | [11 empty] | -- | -- | -- | -- | 20 | 21
20 | [11 empty] | -- | -- | -- | -- | 21 | 21
A simple way to check the validity of Commitment | [15 empty] | 22 | 21
[16 empty] | 23 | 21
[16 empty] | 24 | 21
Original Commitment |  | Team Local Only | ∑Original Estimates for All Planned Cards | [8 empty] | 21 | Points |  |  | 25 | 21
Total Commitment |  |  | ∑Original Estimates for All Cards, whether Planned or Adopted | [8 empty] | 21 | Points |  |  | 26 | 21
Velocity |  |  | ∑Original Estimates for all Cards approved by the SPO by the end of the Sprint | [8 empty] | 21 | Points |  |  | 27 | 21
Work Capacity |  |  | ∑All Work Reported by the Team during the Sprint | [8 empty] | 25 | Points |  |  | 28 | 34
Focus Factor |  | Comparable Between Teams | Velocity ÷ Work Capacity | [8 empty] | 84% | Percent |  |  | 29 | 34
Found Work |  |  | (∑Total Work Reported per Card - That Card's Original Estimate) ÷ Total Commitment | [8 empty] | 4 | Points | 19.05% | Percent | 30 | 34
Adopted Work |  |  | (∑Original Estimates for all Adopted Cards) ÷ Original Commitment | [8 empty] | 0 | Points | 0% | Percent | 31 | 34
Accuracy of Estimation |  |  | 1 - (∑Estimate Deltas ÷ Total Commitment) | [8 empty] | 80.95% | Percent |  |  | 32 | 34
Accuracy of Commitment |  |  | Velocity ÷ (Total Commitment + Found Work) | [8 empty] | 84% | Percent |  |  | 33 | 34
This Sprint would be calculated as a WIN! Your Found + Adopted Work was just 19% of the Original Commitment, and up to 20% is allowable. Also, your Product Owner approved 100% of your Total Commitment. A minimum of 80% is required for a win. | [15 empty] | 34 | 34
[16 empty] | 35 | 34
[16 empty] | 36 | 34
[16 empty] | 37 | 34
[16 empty] | 38 | 34
[16 empty] | 39 | 34
[16 empty] | 40 | 34
[16 empty] | 41 | 34
[16 empty] | 42 | 34
[16 empty] | 43 | 34
[16 empty] | 44 | 34
[16 empty] | 45 | 55
[16 empty] | 46 | 55
[16 empty] | 47 | 55
[16 empty] | 48 | 55
[16 empty] | 49 | 55
[16 empty] | 50 | 55
[16 empty] | 51 | 55
[16 empty] | 52 | 55
[16 empty] | 53 | 55
[16 empty] | 54 | 55
[16 empty] | 55 | 55
[16 empty] | 56 | 55
[16 empty] | 57 | 55
[16 empty] | 58 | 55
[16 empty] | 59 | 55
[16 empty] | 60 | 55
[16 empty] | 61 | 55
[16 empty] | 62 | 55
[16 empty] | 63 | 55
[16 empty] | 64 | 55
[16 empty] | 65 | 55
[16 empty] | 66 | 55
[16 empty] | 67 | 55
[16 empty] | 68 | 55
[16 empty] | 69 | 55
[16 empty] | 70 | 55
[16 empty] | 71 | 55
[16 empty] | 72 | 89
[16 empty] | 73 | 89
[16 empty] | 74 | 89
[16 empty] | 75 | 89
[16 empty] | 76 | 89
[16 empty] | 77 | 89
[16 empty] | 78 | 89
[16 empty] | 79 | 89
[16 empty] | 80 | 89
[16 empty] | 81 | 89
[16 empty] | 82 | 89
[16 empty] | 83 | 89
[16 empty] | 84 | 89
[16 empty] | 85 | 89
[16 empty] | 86 | 89
[16 empty] | 87 | 89
[16 empty] | 88 | 89
[16 empty] | 89 | 89
[16 empty] | 90 | 89
[16 empty] | 91 | 89
[16 empty] | 92 | 89
[16 empty] | 93 | 89
[16 empty] | 94 | 89
[16 empty] | 95 | 89
[16 empty] | 96 | 89
[16 empty] | 97 | 89
[16 empty] | 98 | 89
[16 empty] | 99 | 89
[16 empty] | 100 | 89
[16 empty] | 101 | 89
[16 empty] | 102 | 89
[16 empty] | 103 | 89
[16 empty] | 104 | 89
[16 empty] | 105 | 89
[16 empty] | 106 | 89
[16 empty] | 107 | 89
[16 empty] | 108 | 89
[16 empty] | 109 | 89
[16 empty] | 110 | 89
[16 empty] | 111 | 89
[16 empty] | 112 | 89
[16 empty] | 113 | 89
[16 empty] | 114 | 89
[16 empty] | 115 | 89
[16 empty] | 116 | 89
[16 empty] | 117 | 144
[16 empty] | 118 | 144
[16 empty] | 119 | 144
[16 empty] | 120 | 144
[16 empty] | 121 | 144
[16 empty] | 122 | 144
[16 empty] | 123 | 144
[16 empty] | 124 | 144
[16 empty] | 125 | 144
[16 empty] | 126 | 144
[16 empty] | 127 | 144
[16 empty] | 128 | 144
[16 empty] | 129 | 144
[16 empty] | 130 | 144
[16 empty] | 131 | 144
[16 empty] | 132 | 144
[16 empty] | 133 | 144
[16 empty] | 134 | 144
[16 empty] | 135 | 144
[16 empty] | 136 | 144
[16 empty] | 137 | 144
[16 empty] | 138 | 144
[16 empty] | 139 | 144
[16 empty] | 140 | 144
[16 empty] | 141 | 144
[16 empty] | 142 | 144
[16 empty] | 143 | 144
[16 empty] | 144 | 144

## ExecutionMetrics
Velocity, Work Capacity and Total Commitment (in GREY) are calculated in Story Points and, therefore, cannot be compared between teams. Focus Factor, Adopted Work, Found Work, Targeted Value Contribution Increase, Accuracy of Estimation and Accuracy of Commitment (in BLUE) are calculated in terms of percentages and are fully portable for the purposes of comparing the performance of multiple Teams. The metrics, charts and RoboCoach advice are updated constantly as you enter the data during the Sprint. It is important to note that only those charts on pages 1, 3, 4 and 6 of the Charts tab are useful mid-Sprint. Everything else will be an in-progress calculation until all of the data is entered at the very end of the Sprint. These items are intended for use during the Team's Retrospective as they reflect on how efficient and effective they have been. Remember: RoboScrum can only give you grounds for questions and observations but never for accusations! Talk to your Team, take their feedback and value your collaboration with them over these metrics if the two conflict.
Metric | Used to answer… | Formula
Velocity | How much value can the team plan and achieved to the Product Owner's satsifaction in a sprint? | ∑ Original Estimates of All Approved Cards
Work Capacity | How much effort can the Team expend in a sprint? | ∑ All Work Reported During the Sprint
Total Commitment | How much work did the Team ultimately commit to achieve in the Sprint, including Adopted Work pulled forward after the Planning Meeting? | ∑Original Estimates for All User Stories
Focus Factor | What percentage of the Team's total energy expenditure results in requested-and-approved value? | Velocity ÷ Work Capacity
Adopted Work | As a percentage of the Original Commitment, how much additional work did the Team need to pull forward before the end of the Sprint in order to stay engaged? | (∑ Original Estimates for Work Pulled Forward) ÷ Original Commitment
Found Work | As a percentage of the Original Commitment, how much unexpected complexity did the Team discover mid-Sprint on the work they had already committed to do? | (∑Work Reported per Card - ∑Original Estimates) ÷ Original Commitment
Targeted Value Contribution Increase | How much change has their been in the Team's Velocity over time, since the initial Sprint? (Initial Sprint can be selected on the Setup tab if Team structure changes) | Current Sprint's Velocity ÷ Original Velocity
Accuracy of Estimation | How accurate are the Story Point estimates that the Team provides for their Work? (Takes into account the Fibonacci Shadow, explained on the Fibonacci tab) | 1 - (Estimate Delta ÷ Total Commit)
Accuracy of Commitment | When the Team commits towork, how accurate are they in biting off a block that will keep them busy, at a sustainable pace and be delivered by the end of the Sprint? | (∑Original Estimates) ÷ (∑Original Estimates + ∑Adopted Estimates + ∑Found Work)